## praba
PATIENT PORTAL
S NO | NAME | DATE | TIME | PROJECT TASK | STATUS
1 | praba devi | 28.12.17 | 11 to 4 | documentation on rules on claiming insurance | completed

## sriram
INSURANCE CLAIM ASSESSMENT AND APPROVAL AUTOMATION SYSTEM
S NO | DATE | TIME | PROJECT TASK | STATUS
1 | 2018-12-28 | 11:00 to 16:00 | dummy application creation | in progress
2 | 2018-01-02 | 11:00 to 14:30 | Updating Fields in Application | completed
|  | 14:00 to 16:00 | UiPath Course - 1 | 56% Completed
3 | 2018-01-03 | 11:00 to 12:00 | Automated application login and scrape data fetched from database. Written those scraped data into a csv file using write csv activity | completed
4 | 2018-01-04 | 11:00 to 16:00 | UiPath Course - 1 | 75% Completed
5 | 2018-01-08 | 11:30 to 13:30 | Completed UiPATH course and obtained Certificate | completed
|  | 13:30 to 16:00 | Modified claim Application form | in progress
6 | 2018-01-09 | 11:00 to 14:00 | Problem Solving | -
|  | 14:00 to 16:00 | Modified claim Application form | completed
7 | 2018-01-24 | 11:30 to 17:00 | Configured Mail using outlook mail | completed
8 | 2018-01-25 | 13:00 to 17:00 | Template for mail | completed
9 | 2018-01-29 | 13:00 to 14:00 | Configured mail with attachments | completed
10 |  | 14:00 to 17:00 | Filtering Data from excel | Dropped
11 | 2018-02-05 | 11:00 to 17:00 | Started New workflows and removed older
12 | 2018-02-06 | 11:00 to 17:00 | Created Database and Started Working | completed
13 | 2018-02-07 | 11:00 to 17:00 | Fetched values from db and written in a Excel Sheet | completed
14 | 2018-02-08 | 11:00 to 17:00 | Validated the policy number in claim and policy tables | completed
15 | 2018-02-09 | 11:00 to 17:00 | Worked with NCB check | completed
16 | 2018-02-13 | 11:00 to 16:00 | Calculated Difference for Ws amt and Insured | completed
17 |  | 16:00 to 17:30 | Meeting with mentor at KGFSL | completed
18 | 2018-02-14 | 11:00 to 17:00 | Worked with Vehicle Data and Mail | in progress
19 | 2018-02-15 | 11:00 to 17:00 | Tested the workflow for Vehicle Market Value check and Fixed Bugs | completed

## sudharshan
PATIENT PORTAL
S NO | NAME | DATE | TIME | PROJECT TASK | STATUS
1 | Sudharshan | 28.12.17 | 11:00 to 16:00 | completed 2 Online course chapters in uipath | Completed
2 |  | 2018-01-02 | 11:00 to 14:30 | UiPath course - 1 | 40 percent
3 |  | 2018-01-03 | 11:00 to 12:00 | UiPath course - 1 | 60 percent
4 |  | 2018-01-04 | 11:00 to 16:00 | Variables declaring in bot | 80 percent
5 |  | 2018-01-08 | 11:30 to 13:30 | UiPath course - 1 | 90 percent
6 |  | 2018-01-09 | 11:00 to 14:00 | Policy no DB maintenance
7 |  | 2018-01-24 | 11:30 to 17:00 | Final Test | 100 Percent
8 |  | 2018-01-25 | 13:00 to 17:00 | Policy no check | 100 Percent
9 |  | 2018-01-29 | 13:00 to 14:00 | absent
10
11 |  | 2018-02-05 | 11:00 to 17:00 | Finded duplicate values and eliminates it | 50 percent
12 |  | 2018-02-06 | 11:00 to 17:00 | Finded duplicate values and eliminates it | Finished
13 |  | 2018-02-07 | 11:00 to 17:00 | absent
14 |  | 2018-02-08 | 11:00 to 17:00 | Mail sending using SMTP | Not completed
15 |  | 2018-02-09 | 11:00 to 17:00 | Mail sending using Outlook | Finished
16 |  | 2018-02-13 | 11:00 to 16:00 | Send mail for duplicate values | Finished
17
18 |  | 2018-02-14 | 11:00 to 17:00 | Estimating the workshop price | Finished
19 |  | 2018-02-15 | 11:00 to 17:00 | Maitaining the database for cars | Finished

## prabhakar
PATIENT PORTAL
S NO | NAME | DATE | TIME | PROJECT TASK | STATUS
1 | prabhakar | 28.12.17 | 11 to 4 | absent
2 |  | 2018-01-02 | 11:00 to 14:30 | UiPath course - 1 | 30 percent
3 |  | 2018-01-03 | 11:00 to 12:00 | UiPath course - 1 | 50 percent
4 |  | 2018-01-04 | 11:00 to 16:00 | Variables declaring in bot | completed
5 |  | 2018-01-08 | 11:30 to 13:30 | UiPath course - 1 | 68 percent
6 |  | 2018-01-09 | 11:00 to 14:00 | absent
7 |  | 2018-01-24 | 11:30 to 17:00 | Final Test | 100 Percent
8 |  | 2018-01-25 | 13:00 to 17:00 | Policy no check | completed
9 |  | 2018-01-29 | 13:00 to 14:00 | absent
10
11 |  | 2018-02-05 | 11:00 to 17:00 | vechicle market value calulation | dropped
12 |  | 2018-02-06 | 11:00 to 17:00 | check vechicle estimation | Finished
13 |  | 2018-02-07 | 11:00 to 17:00 | absent
14 |  | 2018-02-08 | 11:00 to 17:00 | vechicle market value calulation | completed
15 |  | 2018-02-09 | 11:00 to 17:00 | absent | Finished
16 |  | 2018-02-13 | 11:00 to 16:00 | absent | Finished
17
18 |  | 2018-02-14 | 11:00 to 17:00 | difference calculation | pending
19 |  | 2018-02-15 | 11:00 to 17:00 | difference calculation | pending