## praba
PATIENT PORTAL
S NO | NAME | DATE | TIME | PROJECT TASK | STATUS
1 | praba devi | 28.12.17 | 11 to 4 | documentation on rules on claiming insurance | completed

## sriram
INSURANCE CLAIM ASSESSMENT AND APPROVAL AUTOMATION SYSTEM
S NO | DATE | TIME | PROJECT TASK | STATUS
1 | 2018-12-28 | 11:00 to 16:00 | dummy application creation | in progress
2 | 2018-01-02 | 11:00 to 14:30 | Updating Fields in Application | completed
|  | 14:00 to 16:00 | UiPath Course - 1 | 56% Completed
3 | 2018-01-03 | 11:00 to 12:00 | Automated application login and scrape data fetched from database. Written those scraped data into a csv file using write csv activity | completed
4 | 2018-01-04 | 11:00 to 16:00 | UiPath Course - 1 | 75% Completed
5 | 2018-01-08 | 11:30 to 13:30 | Completed UiPATH course and obtained Certificate | completed

## sudharshan
PATIENT PORTAL
S NO | NAME | DATE | TIME | PROJECT TASK | STATUS
1 | Sudharshan | 28.12.17 | 11 to 4 | completed 2 Online course chapters in uipath | Completed

## prabhakar
PATIENT PORTAL
S NO | NAME | DATE | TIME | PROJECT TASK | STATUS
1 | prabhakar | 28.12.17 | 11 to 4 | absent