## praba
PATIENT PORTAL
S NO | NAME | DATE | TIME | PROJECT TASK | STATUS
1 | praba devi | 28.12.17 | 11 to 4 | documentation on rules on claiming insurance | completed

## sriram
INSURANCE CLAIM ASSESSMENT AND APPROVAL AUTOMATION SYSTEM
S NO | DATE | TIME | PROJECT TASK | STATUS
1 | 2018-12-28 | 11:00 to 16:00 | dummy application creation | in progress
2 | 2018-01-02 | 11:00 to 14:30 | Updating Fields in Application | completed
|  | 14:00 to 16:00 | UiPath Course - 1 | 56% Completed
3 | 2018-01-03 | 11:00 to 12:00 | Automated application login and scrape data fetched from database. Written those scraped data into a csv file using write csv activity | completed
4 | 2018-01-04 | 11:00 to 16:00 | UiPath Course - 1 | 75% Completed
5 | 2018-01-08 | 11:30 to 13:30 | Completed UiPATH course and obtained Certificate | completed
|  | 13:30 to 16:00 | Modified claim Application form | in progress
6 | 2018-01-09 | 11:00 to 14:00 | Problem Solving | -
|  | 14:00 to 16:00 | Modified claim Application form | completed
7 | 2018-01-24 | 11:30 to 17:00 | Configured Mail using outlook mail | completed
8 | 2018-01-25 | 13:00 to 17:00 | Template for mail | completed
9 | 2018-01-29 | 13:00 to 14:00 | Configured mail with attachments | completed
10 |  | 14:00 to 17:00 | Filtering Data from excel | Dropped
11 | 2018-02-05 | 11:00 to 17:00 | Started New workflows and removed older
12 | 2018-02-06 | 11:00 to 17:00 | Created Database and Started Working | completed
13 | 2018-02-07 | 11:00 to 17:00 | Fetched values from db and written in a Excel Sheet | completed
14 | 2018-02-08 | 11:00 to 17:00 | Validated the policy number in claim and policy tables | completed
15 | 2018-02-09 | 11:00 to 17:00 | Worked with NCB check | completed
16 | 2018-02-13 | 11:00 to 16:00 | Calculated Difference for Ws amt and Insured | completed
17 |  | 16:00 to 17:30 | Meeting with mentor at KGFSL | completed
18 | 2018-02-14 | 11:00 to 17:00 | Worked with Vehicle Data and Mail | in progress
19 | 2018-02-15 | 11:00 to 17:00 | Tested the workflow for Vehicle Market Value check and Fixed Bugs | completed
20 | 2018-02-20 | 11:00 to 17:00 | Worked on Receive mail and tried to filter mails with subject: IMPORTANT | in progress
| 2018-02-21 |  | Review
| 2018-02-22 |  | Re structured and integrated the workflow | completed
| 2018-02-23 |  | Starded working on DB
|  |  | Tried to get a value through text box and printed in next page | in progress
| 2018-02-24 |  | LEAVE
| 2018-02-25 |  | LEAVE
| 2018-02-26 |  | Review Preparation
| 2018-02-27 |  | REVIEW
| 2018-02-28 |  | REVIEW
| 2018-03-01 |  | REVIEW
| 2018-03-02 |  | REVIEW
| 2018-03-03 |  | LEAVE
| 2018-03-04 |  | LEAVE
| 2018-03-05 |  | EXAM
| 2018-03-06 |  | EXAM
| 2018-03-07 |  | EXAM
| 2018-03-08 |  | Created forms and tried to push values to database through forms | completed
| 2018-03-09 |  | automated data update in database through forms | completed
| 2018-03-11 |  | Found bugs in data entry and trying to resolve it | in progress
| 2018-03-12 |  | Found bugs in data entry and trying to resolve it | in progress
| 2018-03-13 |  | Found bugs in data entry and trying to resolve it | in progress
| 2018-03-14 |  | Found alternative method for pushing data to database through build data table | completed
| 2018-03-15 |  | Implemented build datatable method for data pushing | completed
| 2018-03-16 |  | Found errors in pushing data | in progress
2018-03-17
2018-03-18
| 2018-03-19 |  | Trying to resolve bugs | in progress
| 2018-03-20 |  | Resolved bugs | completed
| 2018-03-21 |  | Integrating project and debugging
| 2018-03-22 |  | Integrating project and debugging
| 2018-03-23 |  | Integrating project and debugging
| 2018-03-24 |  | Integrating project and debugging
| 2018-03-25 |  | Integrating project and debugging
| 2018-03-26 |  | Integrating project and debugging

## sudharshan
PATIENT PORTAL
S NO | NAME | DATE | TIME | PROJECT TASK | STATUS
1 | Sudharshan | 28.12.17 | 11 to 4 | completed 2 Online course chapters in uipath | Completed

## prabhakar
PATIENT PORTAL
S NO | NAME | DATE | PROJECT TASK | STATUS | STATUS
1 | 2018-12-28 | 11:00 to 16:00 | dummy application creation | in progress
2 | 2018-01-02 | 11:00 to 14:30 | Updating Fields in Application | completed
|  | 14:00 to 16:00 | UiPath Course - 1 | 56% Completed
3 | 2018-01-03 | 11:00 to 12:00 | Automated application login and scrape data fetched from database. Written those scraped data into a csv file using write csv activity | completed
4 | 2018-01-04 | 11:00 to 16:00 | UiPath Course - 1 | 75% Completed
5 | 2018-01-08 | 11:30 to 13:30 | Completed UiPATH course and obtained Certificate | completed
|  | 13:30 to 16:00 | Modified claim Application form | in progress
6 | 2018-01-09 | 11:00 to 14:00 | Problem Solving | -
|  | 14:00 to 16:00 | Modified claim Application form | completed
7 | 2018-01-24 | 11:30 to 17:00 | Configured Mail using outlook mail | completed
8 | 2018-01-25 | 13:00 to 17:00 | Template for mail | completed
9 | 2018-01-29 | 13:00 to 14:00 | Configured mail with attachments | completed
10 |  | 14:00 to 17:00 | Filtering Data from excel | Dropped
11 | 2018-02-05 | 11:00 to 17:00 | Started New workflows and removed older
12 | 2018-02-06 | 11:00 to 17:00 | Created Database and Started Working | completed
13 | 2018-02-07 | 11:00 to 17:00 | Fetched values from db and written in a Excel Sheet | completed
14 | 2018-02-08 | 11:00 to 17:00 | Validated the policy number in claim and policy tables | completed
15 | 2018-02-09 | 11:00 to 17:00 | Worked with NCB check | completed
16 | 2018-02-13 | 11:00 to 16:00 | Calculated Difference for Ws amt and Insured | completed
17 |  | 16:00 to 17:30 | Meeting with mentor at KGFSL | completed
18 | 2018-02-14 | 11:00 to 17:00 | Worked with Vehicle Data and Mail | in progress
19 | 2018-02-15 | 11:00 to 17:00 | Tested the workflow for Vehicle Market Value check and Fixed Bugs | completed
20 | 2018-02-20 | 11:00 to 17:00 | Worked on Receive mail and tried to filter mails with subject: IMPORTANT | in progress
21 | 2018-02-21 |  | Review
22 | 2018-02-22 |  | Re structured and integrated the workflow | completed
23 | 2018-02-23 |  | Starded working on DB
24 |  |  | Tried to get a value through text box and printed in next page | in progress
25 | 2018-02-24 |  | LEAVE
26 | 2018-02-25 |  | LEAVE
27 | 2018-02-26 |  | Review Preparation
28 | 2018-02-27 |  | REVIEW
29 | 2018-02-28 |  | REVIEW
30 | 2018-03-01 |  | REVIEW
31 | 2018-03-02 |  | REVIEW
32 | 2018-03-03 |  | LEAVE
33 | 2018-03-04 |  | LEAVE
34 | 2018-03-05 |  | EXAM
35 | 2018-03-06 |  | EXAM
36 | 2018-03-07 |  | EXAM
37 | 2018-03-08 |  | Created forms and tried to push values to database through forms | completed
38 | 2018-03-09 |  | automated data update in database through forms | completed
39 | 2018-03-11 |  | Found bugs in data entry and trying to resolve it | in progress
40 | 2018-03-12 |  | Found bugs in data entry and trying to resolve it | in progress
41 | 2018-03-13 |  | Found bugs in data entry and trying to resolve it | in progress
42 | 2018-03-14 |  | Found alternative method for pushing data to database through build data table | completed
43 | 2018-03-15 |  | Implemented build datatable method for data pushing | completed
44 | 2018-03-16 |  | Found errors in pushing data | in progress
45 | 2018-03-17
46 | 2018-03-18
47 | 2018-03-19 |  | Trying to resolve bugs | in progress
48 | 2018-03-20 |  | Resolved bugs | completed
49 | 2018-03-21 |  | Integrating project and debugging
50 | 2018-03-22 |  | Integrating project and debugging
51 | 2018-03-23 |  | Integrating project and debugging
52 | 2018-03-24 |  | Integrating project and debugging
53 | 2018-03-25 |  | Integrating project and debugging
54 | 2018-03-26 |  | Integrating project and debugging